## Schedule
Schedule | Hours | Goal | Accomplishments | Tasks
December 14th | 0 | Obtained Group Assignments
December 16th | 1 | Establish project theme and potential data sources | Selected Politics, specifically Election Data | Search for comprehensive dataset and potential graphics
December 18th | 3.5 | Evaluate data sources and determine project structure | Found good dataset and supporting datasets | Determine if geoJSON data is available for county and district maps; determine types of plots that can be derived from data; setup Heroku and Github
December 21th | 3 | Setup Git Repository and Heroku Format Data and import to Postgres Create charts: * Bubble Plot * Radial Plot / Branch Plot (Erin) * Map Plot * Heat Map/Chloropleth * Plotly with webscrape/JSON 'Live' Data
December 23th | 3
?Mid-Break Meeting? Jan. 27?+/-
January 4th | 3
January 6th | 3 | Wrap-up (Presentations, final touchups, graphs, Heroku deployment tests)
January 8th | 3 | Project Presentations

## Requirements
| Custom D3.js Visualization | Webscraping with Leaflet or Plot.ly | Dashboard page with Multiples Charts updating from same info
One Database (SQL, MongoDB, SQLite, etc.). |  |  | Postgres (via Heroku)
Python Flask–powered RESTful API |  |  | Yes
HTML/CSS |  |  | template html (python-flask)
JavaScript |  |  | D3/Plot.ly
JavaScript (new library) |  |  | masonry, highcharts, etc
3 Views | Maybe (Erin has a D3 chart he would like to make) |  | ??? TBD ???
Data of > 100 Rows |  |  | Yes
User Interaction |  |  | ??? Selectors ???
Categories
Politics

## Resources
Past Election Results | https://transition.fec.gov/pubrec/electionresults.shtml
https://www.270towin.com/
https://electionlab.mit.edu/data
https://www.kaggle.com/benhamner/2016-us-election
https://www.kaggle.com/stevepalley/2016uspresidentialvotebycounty
https://www.kaggle.com/c/predict-donald-trump-s-election-success-by-county/data
https://www.nytimes.com/interactive/2019/04/22/upshot/upshot-at-five-years.html?mtrref=www.google.com&assetType=REGIWALL
https://www.cnn.com/election/2016/results
https://guides.lib.umich.edu/c.php?g=282896&p=1885080
Demographics
Population | https://data.census.gov/cedsci/
Branching Categorization | http://archive.nytimes.com/www.nytimes.com/interactive/2012/11/02/us/politics/paths-to-the-white-house.html
Change graphic | https://archive.nytimes.com/www.nytimes.com/interactive/2012/11/11/sunday-review/counties-moving.html
US County Map | http://blog.thehumangeo.com/2014/04/21/whats-new-in-the-leaflet-dvf/
https://leafletjs.com/examples/choropleth/
Bureau of Labor Statistics | https://console.cloud.google.com/marketplace/browse?filter=solution-type:dataset&_ga=2.261757005.-1573274697.1576646056&pli=1
US Residential Real Estate Data by HouseCanary
Medicare Stats
FEC Campaign Finance
Hospital General Information
Political Advertising on Google
US Census
https://github.com/unitedstates/districts

## Brainstorming
Plot.ly | chloropleth sign